## Gantt Chart
EGT GANTT CHART
PROJECT TITLE |  | The Binding of Saw |  |  |  | UNIVERSITY |  | Anglia Ruskin University
PROJECT MANAGERS |  | Matthew Stageman and Tom Tse |  |  |  | START DATE |  | 2018-09-24
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DURATION | PCT OF TASK COMPLETE | PHASE 1 - RESEARCH AND GREYBOXING |  |  |  | PHASE 2 - DEVELOPING |  |  | PHASE 3 - IMPLEMENTING TECHNOLOGY |  |  | PHASE 4 - TESTING AND DOCUMENTS
[6 empty] | Week 1 | Week 2 |  | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
1 | Decide on idea and technologies | Both | 1 | 3 | 100%
2 | HTC VIVE research | Both | 2 | 2 | 100%
3 | Leap Motion Technology Research | Both | 2 | 2 | 100%
4 | Shaders research | Both | 2 | 2 | 100%
5 | Microphones and audio commands research | Both | 2 | 2 | 100%
6 | Procedural generation research | Both | 2 | 2 | 100%
7 | Random generation research | Both | 2 | 2 | 100%
8 | Create simple grey box | Matt | 2 | 1 | 100%
9 | Implement procedural generation of rooms | Tom | 3 | 4 | 100%
10 | Implement Timed system | Matt | 4 | 1 | 100%
11 | Implement Random generation for challenges | Matt | 5 | 1 | 100%
12 | Creating Main menu and Lose/Win condition | Matt | 4 | 3 | 100%
13 | Creating Challenge 1 | Matt | 6 | 3 | 100%
14 | Creating Challenge 2 | Tom | 6 | 3 | 100%
15 | Creating Challenge 3 | Tom | 8 | 3 | 100%
16 | Creating Challenge 4 | Matt | 8 | 3 | 100%
17 | Implementing VR | Tom | 7 | 3 | 100%
18 | Implementing Leap motion | Matt | 7 | 3 | 100%
19 | Getting the Leap motion and VR to work with challenges | Both | 7 | 5 | 100%
20 | Creating voice recognizer for challenge 4 | Matt | 9 | 2 | 100%
21 | Creating a custom shader (Glitch shader) | Matt | 9 | 2 | 100%
22 | Creating Design Document | Both | 10 | 3 | 100%
23 | Creating Evaluations | Both | 10 | 3 | 100%
24 | Creating User Guide | Both | 10 | 3 | 100%
25 | General Testing | Both | 7 | 6 | 100%